## Sheet1
Stand up meeting date: 16/ 02/ 2024
Team's name | Group 04 E-classroom
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
senghak chhun | review code | 4h | 4h | create sign in feature | 4 h
rady doeurn | Design home page | 4h | 4h 10m | sigup interface | 1 h40m
theun en | search about how to send notifications | 4h | 4h 30m | create home page after create account | 2h 20m
sreymon chak | design card | 4h | 3h 20m | create general page before create account | 2h 20m
sreynang rith | review code | 4h | 4h | create login page | 1h 40m